## Introduction (hidden)
Construction Delivery Form
Site Manager's Guide
CDFR14-17
Revision 3
Site Manager's Guide
Introduction
This guide for Site Managers has been developed to assist in settting out the tasks that need to be undertaken and their frequency in support of procedures, flowcharts and guidance available on the MWHT Way but it is in no way exclusive and regional variations may be in place.
The forms referenced within the guide are available on the MWHT Way with some in the Construction Site Briefcase or on BIM Field.
MACROS MUST be enabled for full interactive use of this document, click here for instructions to enable
If you need further assistance or have any queries please contact your Regional Quality Manager or the SHEQ Team in the Soapworks.
Macros
Start

## Start
Construction Delivery Form
Site Manager's Guide
CDFR14-17
Revision 3
Site Set Up
Daily
Weekly
2 - Weekly
Monthly
3 Monthly
6 Monthly
Task Specific
Others
Copies Required
Guide
Click on any of the links below to see what should be completed by a Site Manager in that period.
Where 'Task Specific' items are required on site these items may also need to be completed Daily, Weekly, etc.
To add these items to the appropriate listing pick from the drop down list to reassign location.
Show All

## MACRO inst (hidden)
1
Start
File, Options
Select Customise Ribbon
Check The Developer Box, Click OK
On The Ribbon Select Developer
Select Macro Settings and Check The Enable All Macros, Click Ok, Close the workbook, re-open and Press The Start Button

## Listings (hidden)
Form reference | Form Title | Frequency | Notes
CDFR02-03 | Project Inspection & Test Plan | Task Specific | Check & verify before mapping to BIM
CDFR02-08 | Reg 31 Schedule of material in contact with potable water | Daily | Water sites only | Site Set up
CDFR02-10 | HAZCON Action Record | Task Specific | Where HAZCON completed | Task Specific
CDFR04-01 | Site Filing Index Sheets (Regional equivalent) | Site Set up | If not exclusively using BIM | Weekly
CDFR07-01 | Document Schedule (Regional equivalent) | Weekly | Check against receipts & use for status check | Daily
CDFR11-01 | Internal Safe System of Work, Review Checklist and Briefing | Task Specific | also on BIM360 Field, but Brief and hold points signs off ONLY | Monthly
CDFR11-02 | Safety Risk Assessment | Task Specific |  | Copies Required
CDFR11-03 | Contractor Safe System of Work Review Checklist and Briefing | Task Specific |  | 6 monthly
CDFR11-05 | Safe Systems of Work Register | Task Specific |  | Other
CDFR11-06 | Minor Change Record | Task Specific | also on BIM360 Field | 3 Monthly
CDFR12-01 | Technical Query Form | Task Specific | For queries against information supplied | 2-weekly
CDFR12-02 | Technical Query Register | Task Specific
CDFR14-03 | Considerate Constructors Action Plan | Task Specific | Where signed up to CC
CDFR14-07 | Monthly SHEQ Review | Monthly | Invite Safety Advisor & Construction Manager also on BIM360 Field
CDFR14-08 | Site Diary | Daily | also on BIM360 Field
CDFR16-02 | Subcontractor Pre-Commencement Meeting | Task Specific | All sub-contractors
CDFR16-03 | Subcontractor ITP Appraisal Form | Task Specific | All sub-contractors (as required)
CDFR17-03 | Instrument Check Record | Task Specific | As defined by CDFR41-01 also on BIM360 Field
CDFR17-04 | TBM Schedule | Task Specific
CDFR17-05 | Survey Check Record | Task Specific
CDFR18-01 | Permit to Pump Concrete | Task Specific | also on BIM360 Field
CDFR18-04 | pH Monitoring Log | Task Specific | also on BIM360 Field
CDFR20-03 | Appointment of Site Safety & Environmental Supervisor | Site Set up | Sign & Return
CDFR20-05 | Delegation Of Site Safety and Environmental Supervisor Duties | Task Specific | Where delegating duties also on BIM360 Field
CDFR20-07 | Site Safety and Environmental Checklist | Weekly
CDFR20-12 | Pre-Site Start-Up Meeting Agenda | Site Set up
CDFR20-13 | Site Signing In/Out Sheet | Daily
CDFR20-16 | Record of Project Handover Between Site Managers | Task Specific | For all planned absences
CDFR23-09 | Commissioning Plan (Regional equivalent) | Copies Required
CDFR23-12 | Commissioning Training Plan | Copies Required
CDFR23-13 | HazComm Sheet | Copies Required | by Commissioning Engineer/PM, may affect ITP, SM to address any actions required
CDFR23-21 | Hazard Study 5 Report | Copies Required | by Commissioning Engineer, SM to address any actions required
CDFR23-24 | Commissioning Statement | Copies Required | by Commissioning Engineer, SM to address any actions required
CDFR23-25 | Hazard Study 6 Report | Copies Required | by Commissioning Engineer, SM to address any actions required
CDFR24-01 | Temporary Works Design Brief | Task Specific | also used for Temp Works design check request
CDFR24-02 | Temporary Works Design Review Record | Task Specific
CDFR24-04 | Appointment of Temporary Works Supervisor | Task Specific | Copy required on site
CDFR24-05 | Appointment of Temporary Works Co-ordinator | Task Specific | Copy required on site
CDFR24-06 | Temporary Works Inspection Record and Permit | Task Specific | Refer to Temp Works Schedule
CDFR24-08 | Stockpile Inspection Record | Task Specific
CDFR28-01 | Basic Lifting Plan | Task Specific
CDFR28-02 | Intermediate Lifting Plan and Permit to Lift | Task Specific
CDFR28-03 | Letter of Appointment for Appointed Person Lifting | Copies Required
CDFR28-05 | Complex Lift Plan | Task Specific
CDFR28-06 | Letter of Appointment for Crane Operations Supervisor | Copies Required
CDFR28-08 | Local Lifting Arrangements | Task Specific
CDFR28-09 | Lorry Loader Crane Basic Lift Plan | Task Specific | also on BIM360 Field
CDFR28-10 | Lifting Equipment - Weekly Inspection Report | Weekly | also on BIM360 Field
CDFR28-11 | Lifting Equipment - Record of Thorough Examination Certificates | Copies Required
CDFR30-01 | Site Visitor Induction | Task Specific | For use where preferred online induction not available CDFR30-01 and CDFR30-02 also on BIM360 Field
CDFR30-02 | Contractor Induction Assessment Questionnaire | Task Specific
CDFR30-03 | Site Induction Training Record | Site Set up
CDFR30-04 | Induction Training Register | Task Specific
CDFR30-05 | Plant Operators - Competence Certificates | Copies Required | Where not captured on online induction
CDFR30-06 | Site Daily SHEQ Briefing | Daily
CDFR30-07 | Safe Start Card | Daily
CDFR30-08 | Toolbox Talk Attendance Register | Task Specific | also on BIM360 Field
CDFR30-09 | Contractor Supervisors Induction | Task Specific
CDFR30-10 | Delivery Drivers Induction | Task Specific
CDFR32-01 | Fire Risk Assessment | Site Set up | Maintain & keep up to date
CDFR32-02 | Fire Safety Plan | Site Set up | Maintain & keep up to date
CDFR32-03 | Fire Action Notice | Site Set up | To be displayed
CDFR32-04 | Emergency Contacts | Site Set up | Maintain & keep up to date
CDFR32-05 | Evacuation Drill Report | Site Set up | Then at 6-monthly intervals also on BIM360 Field
CDFR32-05 | Evacuation Drill Report | 6 monthly | also on BIM360 Field
CDFR33-01 | Weekly Site Fencing Inspection | Weekly
CDFR33-02 | Manual Lift Arm Barrier Check Sheet (if applicable) | Weekly
CDFR34-01 | Excavation / Cofferdam Inspection Report | Daily | Weekly sign off required also on BIM360 Field
CDFR34-02 | CAT & Genny Assessment Form | Task Specific
CDFR35-01 | Ground Disturbance Permit | Task Specific
CDFR35-02 | Hot Works Permit | Task Specific
CDFR35-03 | General Permit to Work (G Permit) | Task Specific
CDFR35-04 | Permit to Work Register | Task Specific | Covers all permits
CDFR35-06 | Permit to work on or near above ground services | Task Specific
CDFR35-07 | General Isolation Certificate | Task Specific
CDFR35-08 | Significant Risk Operations Permit | Task Specific
CDFR36-01 | Road and Street Works - Site Checklist | Task Specific
CDFR37-01 | Excavator Quick Hitch Attachment Register | Task Specific | also on BIM360 Field
CDFR37-02 | Excavator Operator's Declaration Form | Task Specific | To be completed on arrival on site also on BIM360 Field
CDFR37-03 | Excavator Operator Questionnaire | Task Specific | To be completed on arrival on site also on BIM360 Field
CDFR37-04 | Safe Use of Excavator Quick Hitch Checklist | Task Specific | To be completed on arrival on site also on BIM360 Field
CDFR38-01 | Hand Arm Vibration Assessment | Task Specific | Complete for each task involving HAVS
CDFR38-02 | Vibration Dose Assessment | Task Specific | Record of exposure
CDFR39-01 | Noise Assessment Register | Task Specific | Complete for each task where noise levels indicate
CDFR39-02 | Noise Assessment Record | Task Specific | Record of exposure also on BIM360 Field
CDFR39-03 | Environmental Noise Monitoring Record | Task Specific
CDFR40-01 | Working Platforms, Scaffolds and Personal Suspension Equipment Inspection Register | Task Specific | Weekly if in use on site (and prior to first use)
CDFR40-02 | Ladder Inspection Register | Weekly | also on BIM360 Field
CDFR40-03 | Mobile Tower Inspection Checklist | Task Specific | Daily if in use on site also on BIM360 Field
CDFR41-01 | Equipment Register | Task Specific | in addition to the PUWER Register
CDFR43-02 | Outstanding Works | Task Specific
CDFR43-04 | Certificate of Construction Completion | Copies Required | PM responsibility, SM to be made aware/copy
CDFR43-05 | Plant In Use Agreement | Copies Required
CDFR43-06 | Plant In Use - SCADA and eSCADA Checklist | Task Specific
SYFR07-01 | Improve It Card | Task Specific | Regional targets. Also on ActivSHEQ.
SYFR07-02 | Internal Accident Notification | Task Specific | Initial report only. Upload to ActivSHEQ.
SYFR07-03 | Property Damage and Loss Report | Task Specific | Initial report only. Upload to ActivSHEQ.
SYFR07-04 | Violent Incident Report | Task Specific | Initial report only. Upload to ActivSHEQ.
SYFR07-06 | Environmental Incident Report | Task Specific | Initial report only. Upload to ActivSHEQ.
SYFR07-08 | Accident Information Checklist | Task Specific | Initial report only. Upload to ActivSHEQ.
SYFR08-02 | Statement of Witness | Task Specific | As requested by SHEQ Advisor. Upload to ActivSHEQ.
HSFR01-01 | Construction Phase Plan | Other | Input may be requested prior to site set up
HSFR01-10 | Key Duty Holders List | Site Set up
HSFR01-11 | Consultation Poster | Site Set up
HSFR02-02 | Confined Space Permit to Enter | Task Specific
HSFR02-04 | Confined Space Entry Log | Task Specific
HSFR02-05 | Confined Space Managers Checklist | Task Specific
HSFR03-01 | Hazardous Materials Inventory | Task Specific | Copy also to be displayed in storage area
HSFR03-02 | Face Fit Test Record | Task Specific | Annual test required
HSFR03-03 | COSHH Assessment Form | Task Specific
HSFR03-04 | COSHH Training Register (on BIM ONLY) | Task Specific | on BIM360 Field only
HSFR05-01 | Isolation Device Register | Task Specific
HSFR06-03 | Electrical Audit Inspection Report (or regional equivalent) | Copies Required | Managed by Electrical Supervisor (SAP)
HSFR06-04 | Initial Site Electrical Safety Risk Report (or regional equivalent) | Copies Required | Managed by Electrical Supervisor (SAP)
HSFR06-05 | Competent Person Register (or regional equivalent) | Copies Required | Managed by Electrical Supervisor (SAP)
HSFR06-07 | Permit to Enter | Copies Required | Managed by Electrical Supervisor (SAP)
HSFR06-08 | Electrical Permit to Work (or regional equivalent) | Copies Required | Managed by Electrical Supervisor (SAP)
HSFR06-09 | Electrical Sanction to Live Test (or regional equivalent) | Copies Required | Managed by Electrical Supervisor (SAP)
HSFR06-10 | Limitation of Access for Non-electrical Work (or regional equivalent) | Copies Required | Managed by Electrical Supervisor (SAP)
HSFR06-12 | Electrical Permit Register (or regional equivalent) | Copies Required | Managed by Electrical Supervisor (SAP)
HSFR06-14 | Electrical Isolation Document (or regional equivalent) | Copies Required
HSFR06-15 | Site Electrical Folder Index | Copies Required
HSFR06-16 | Electrical Authorised Person Certificate (or regional equivalent) | Copies Required
HSFR07-01 | PPE Issue Register | Task Specific | also on BIM360 Field
HSFR07-04 | Safety Eyewear Form | Task Specific | For prescription safety eyewear
HSFR08-02 | Asbestos Contractor Site Checklist | Task Specific
HSFR09-01 | Task Specific Manual Handling Assessment | Task Specific
HSFR13-01 | New or Expectant Mothers Risk Assessment | Task Specific | also contact Safety Advisor / HR
HSFR13-02 | Return to Work Risk Assessment | Copies Required
HSFR15-01 | Work Equipment Inspections Register | Task Specific | PUWER Register also on BIM360 Field
HSFR15-02 | Plant Operator's - Daily Inspection Checklist | Daily | also on BIM360 Field
HSFR15-03 | Abrasive Wheels Register | Task Specific
HSFR15-04 | Portable Tools Check | Task Specific | PUWER form for small tools also on BIM360 Field
HSFR15-05 | Dumper Weekly Checklist | Daily | also on BIM360 Field
HSFR15-06 | Excavator Weekly Checklist | Daily | also on BIM360 Field
HSFR15-07 | Roller Weekly Checklist | Daily | also on BIM360 Field
HSFR15-08 | Telehandler Weekly Checklist | Daily | also on BIM360 Field
HSFR15-09 | Mobile Elevated Working Platforms | Daily | also on BIM360 Field
HSFR15-11 | Fork Lift Truck Weekly Checklist | Task Specific | also on BIM360 Field
HSFR15-12 | Harness Inspection Report | 3 Monthly | Recorded 3 monthly but visual check before use also on BIM360 Field
HSFR15-13 | Vacuum Excavator Checklist | Daily
HSFR17-01 | First Aider / Fire Marshall / Metal Health First Notice | Site Set up | To be displayed
HSFR17-02 | Automated external defibrillator (AED) – Monthly Checklist | Monthly | also on BIM360 Field
HSFR17-03 | First Aid Risk Assessment | Task Specific
HSFR17-04 | First Aid Kit Inspection | Other
HSFR18-01 | Electrical Appliance (PAT) Register | Task Specific | Refer to HSGD18-01 Guidelines for frequency
HSFR18-04 | Electrical Appliance Fault Register | Task Specific
HSFR19-03 | DSEAR ATEX Verification Report | Copies Required | If Applicable
HSFR19-05 | Certificate of Appointment - DSEAR Responsible Person | Copies Required | If Applicable
HSFR19-06 | DSEAR Working in Live Hazardous Areas | Task Specific | Site Manager or DSEAR Responsible Person
HSFR22-01 | Assessment and Appointment of Mechanical Authorised Person | Task Specific | by Mechanical Authorising Engineer
HSFR22-02 | Limitation of Access Around Mechnical Systems | Task Specific | by Mechanical Authorised Person
HSFR22-04 | Pressure Test Check Sheet | Task Specific | by Mechanical Authorised Person
HSFR22-05 | Pressure Test Permit to Work | Task Specific | by Mechanical Authorised Person
HSFR22-06 | Pressure Test Register | Task Specific | by Mechanical Authorised Person
HSFR22-07 | Pressure Test Report | Task Specific | by Mechanical Authorised Person
EVFR01-01 | Environmental Management Plan Part A - Site Specific | Copies Required | Draft version by PM, quarterly updates by SM
EVFR01-01 | Environmental Management Plan Part A - Site Specific | 3 Monthly | Draft version by PM, quarterly updates by SM
EVFR01-01b | Environmental Management Plan Part B - Mandatory Requirements | Copies Required
EVGD01-08 | Environmental Constraints Map | Site Set up | In conjunction with Environmental Advisor
EVFR01-07 | Invasive Plant Management Plan | Task Specific | In conjunction with Environmental Advisor
EVFR01-08 | Invasive Plant Recording Sheet | Task Specific | In conjunction with Environmental Advisor also on BIM360 Field
EVFR01-10 | Environmental Management Plan Briefing Record | Site Set up
EVFR01-11 | Calculating Root Protection Areas | Task Specific
ActivSHEQ | Site Material and Waste Management Plan | Site set up | Keep updated as required (on ActivSHEQ)
ActivSHEQ | Site Material and Waste Management Plan | 6 monthly | Keep updated as required (on ActivSHEQ)
EVFR03-04 | Waste Transfer Note | Copies Required | Where not provided by waste carrier
EVFR03-05 | Hazardous Waste Consignment Note | Copies Required
EVFR03-06 | Waste Duty of Care Checklist | Task Specific | Where deemed appropriate - to review quality of waste duty of care documentation
PSFR03-09 | Project Sustainability and Social Value Plan (PSSVP) | Copies Required | PM responsibility. Where required (set criteria) to be started at tender stage - to continue through design and operations
PSFR03-11 | Design Build Sustainability and Carbon Checklist | Copies Required | PM responsibility. Started at tender stage - to continue through design and operations
EVFR06-02 | Site Carbon Smart Checklist | Site Set up | Medium & Large sites and those with a Project Sustainability and Social Value Plan (PSSVP)
EVFR06-02 | Site Carbon Smart Checklist | Task Specific
EVFR04-01 | Site Environmental Emergency Plan | Site set up | Review required by Environmental Advisor
EVFR04-02 | Spill Drill Record | 6 monthly | Within 3 months of site start and then at least annually
EVFR04-03 | Site Flood Plan | Copies Required
EVFR04-04 | Silt Drill Record | Task Specific | Frequency as determined in EMP
EVFR04-14 | Frac Out Plan | Task Specific | Produced with Environmental Advisor and Drilling Contractor
EVFR05-03 | Permit to Pump to Ground (England and Wales) | Task Specific | also on BIM360 Field
EVFR05-04 | Dewatering to Surface Waters Checklist (Eng and Wales) | Task Specific
EVFR05-05 | Permit to Pump to Ground (Scotland) | Task Specific
EVFR05-06 | Watercourse Monitoring Record | Task Specific | Frequency as determined in EMP also on BIM360 Field
EVFR05-12 | Record of Water Abstractions | Task Specific
EVFR05-07 | Schedule of Planning Conditions | Copies Required
EVFR05-08 | Overpumping Permit | Task Specific
EVFR05-12 | EVFR05-12 Record of Water Abstractions | Task Specific | Frequency determined with Environmental Advisor
EVFR05-13 | Licence / Consent / Permit - Briefing Record | Task Specific | Briefing with Environmental Advisor
PSFR03-06 | Temporary Works Schedule | Site set up | Review before project start and keep up to date by TWC
PSFR03-06 | Temporary Works Schedule | Task Specific | Review before project start and keep up to date by TWC
| Self-Assessment Questionnaire for DSE Users | Site Set up | via activSHEQ
| SM Update Call (regional specific, e.g. Genba in ST Region) | Daily | May vary depending on regional requirements
| PM / SM Call | 2-weekly | May vary depending on regional requirements
| Collaborative Planning | Monthly | May vary depending on regional requirements
| Project Update Discusstion (e.g. Comm Cell in ST region) | Weekly | Can be weekly or monthly depending on the Client's requirements
| Site Return - Manhours | Monthly | via activSHEQ, prompted by e-mail monthly
Back to Start